## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | term-swen-261-02-A Java 19
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want my shopping cart to persist through browsing sessions so I can resume my session later. | Given I am logged in and there are items in my cart when I log out of the store and log in later then I should see that the same cart remains populated in my account | Pass | JE 3/10/23
As a developer I want to be able to save a customer’s cart information to the backend so that I can keep track of what the user is trying to purchase. | Given I am a customer when I add an item to my cart, then I should see that item and its price appear in my cart | Pass | AP 3/15/23
| Given I am a customer when I remove an item from my cart, then I should see that the item no longer exists in my cart | Pass | AP 3/15/23
As a developer I want to be able to send and receive customer data with the backend API so that I can represent that information in the frontend. | Given I am the frontend when I want to create a new user then I should be able to accomplish that by sending an API call to the backend | Pass | AS 3/17/23
| Given I am the frontend when I want to edit a user then I should be able to send an API call to the backend to edit that user | Pass | AS 3/17/23
| Given I am the frontend when I want to delete a user then I should be able to delete the user through an API call | Pass | AS 3/17/23
As an owner I want only those authorized to be able to access the inventory. | **Given** I input the correct username and password **when** I login **then** I will be able to access owner permissions. | Pass | JL 3/19/23
As a developer I want to be able to send and receive information about an order so that I can display a customer’s current order status | **Given** I am creating an order **when** I go to checkout **then** I expect to see the products in my order, the total price, and the time/date of the order | Pass | ML 3/12/23
As an owner I want to edit customer orders so that I can mark orders as complete or refund them if there is a problem. | **Given** that I have owner permission **when** I click on a order on the list **then** I will be given options to remove or mark orders complete. | Pass | ML 3/11/23
| **Given** that I have owner permission **when** click on the remove button **then** the order will be deleted from the list. | Pass | ML 3/11/23
| **Given** that I have owner permission **when** click on the complete order button **then** the order will be marked as complete. | Pass | ML 3/11/23
As an owner I want to add and remove inventory so there is an accurate representation of products | **Given** that I have owner permission **when** I click on a product in the inventory **then** I will be given options to delete or edit specific details about the product. | Pass | JL 3/15/23
| **Given** that I have owner permission **when** click on the delete button **then** the product will be deleted from the estore. | Pass | JL 3/15/23
As an owner I want to edit product details so that I can update products descriptions | **Given** that I have owner permission **when** click on the edit button for a product **then** I will be able to edit the attributes of the product. | Pass | AP 3/17/23
| **Given** that I have owner permission **when** I click on a product in the inventory **then** I will be given options to delete or edit specific details about the product. | Pass | AP 3/17/23
| **Given** that I have owner permission **when** click on the delete button **then** the product will be deleted from the estore. | Pass | AP 3/17/23
As a user I want to see navigation options so that go to where I want on the site. | Given I am logged in when go to the website then I will be presented with links that route to other parts of the webpage. | Pass | AS 3/18/23
As a buyer I want to see a list of products so I can choose what to purchase. | Given the inventory of the shop is selected when I look at the contents of the inventory then I can see the list of products that the store is maintaining | Pass | AP 3/16/23
As a user I want to be able to have an account so that I can track my cart and orders. | Given I am not logged in when I click "add to cart" on a item then I should be prompted to log in. Given I am not logged in when input my login details on the login page then it should log me in. | Pass | JL 3/15/23
As a buyer I want to search for a specific product so I can effectively search for a product in the store. | Given I am looking for a specific product when I search for the name of the product in the store then I expect a list of matching products to be reported to me | Pass | ML 3/19/23
As a buyer I want to be able to add and delete products to a cart so I can pick the products I receive. | Given I am a user logged in to the store when I plan to purchase an item then I should be able to add it to my cart | Pass | JE 3/20/23
| Given I am a user logged in to the store and there are items in my shopping cart when I try to remove items from my cart then the item I remove should be dropped from the cart.. | Pass | AP 3/19/20
As a buyer I want to be able to check out so I can purchase the items in my cart. | Given I have items in my shopping cart when I try to checkout all the items in my cart then I should proceed to a checkout dialogue to purchase my products | Pass | JE 3/20/23
| Given I have items in my shopping cart when I complete checkout then my order should complete and the store owner should be able to fulfill my order | Pass | JE 3/20/23
As an owner I want to see a list of customer orders so that I can fulfill those customer orders. | **Given** that I have owner permission **when** I click on the orders tab on the estore site **then** I will be moved to the orders page. **Given** that I have owner permission **when** I view the order page **then** I will be given a list of all the customer orders. | Pass | JE 3/16/23